See e-mail distribution list

Wednesday 12th March 2008

#### LNW ROTR Changes for WCRM Enhancements (Proposal)

Dear All,

I have been approached by colleagues in the WCRM project for alterations to the possession access required to deliver WCRM enhancements. Outlined below are the proposed changes to the 2008 and 2009 LNW Rules of the Route, as discussed at our meeting in Crewe today.

LNW 2008 ROTR section 4 possessions to be amended to read:

MD101 EUSTON TO ARMITAGE JN

101.7 Bletchley South Jn and Hanslope Jn, Weekend period ‘C’ amended to read: 2330 Fri to 0700 Sat Fasts BLOCKED and 2000 Sat to 0530 Mon Slows BLOCKED and 0020 Sun to 0935 Sun (currently 0110 Sun-0915 Sun) All BLOCKED Weekend electrical isolations of Bletchley DF Parcel Sidings to be lifted by 0830 Sun Weekend electrical isolations of Bletchley CS & TMD to be lifted by 0330 Mon (Network Rail Request). (proposed amendment in blue).

NOTE: 2215 Sat to 0400 Mon no slow access Bletchley station and no access Bletchley CS.

101.10 Hillmorton Jn and Trent Valley Jn, Weekend period ‘D’ amended to read 1000 Sat to 0935 Sun All BLOCKED (currently 2340 Sat-0935 Sun), and weekend period ‘E’ amended to read 2210 Sat to 0945 Sun (Network Rail Request).

101.11 Trent Valley Jn and Nuneaton South Jn, Weekend period ‘D’ amended to read 1000 Sat to 0930 Sun All BLOCKED (currently Period D1 1045 Sat-0930 Sun, Period D2 2330 Sat-0910 Sun), (Network Rail Request).

101.12 Nuneaton South Jn and Nuneaton North Jn, Weekend period ‘D’ amended to read 1000 Sat to 0930 Sun All BLOCKED (currently Period D1 1045 Sat -0930 Sun, Period D2 0001 Sun-0910 Sun) (Network Rail Request).

101.13 Nuneaton North Jn and Tamworth Low Level, Weekend period ‘D’ amended to read 1000 Sat to 0930 Sun All BLOCKED (currently Period D1 1000 Sat -0930 Sun, Period D2 2330 Sat – 0845 Sun) (Network Rail Request).

101.14 Tamworth Low Level and Lichfield Trent Valley Jn, Weekend period ‘D’ amended to read 1000 Sat to 0930 Sun All BLOCKED (currently Period D1 1000 Sat -0930 Sun, Period D2 2330 Sat – 0845 Sun) (Network Rail Request).

101.15 Lichfield Trent Valley Jn and Armitage Jn, Weekend period ‘D’ amended to read 1000 Sat to 0930 Sun All BLOCKED (currently Period D1 1000 Sat – 0930 Sun, Period D2 2330 Sat-0830 Sun) (Network Rail Request).

NOTE: Existing ROTR in period D1 are for the Trent Valley to be BLOCKED 1000 Sat to 0930 Sun.

Clashing Possessions:

Weeks 10, 11, 12, 13 Freightliner diversions cross country.

MD301 RUGBY TRENT VALLEY JN TO PENKRIDGE (VIA BIRMINGHAM)

301.1 Trent Valley Jn and Coventry South Jn, Weekend period ‘D’ amended to read 0045 Sat to 0500 Mon BLOCKED (V6.2 Period D1 2350 Sat – 0500 Mon, Period D2 0045 Sat-0500 Mon) Electrical isolations Rugby to Coventry North to be lifted by 0450 Mon (Network Rail Request).

301.2 Coventry South Jn to Coventry North Jn, Amend footnote to read:   	Weekend week 8 (w/c Sat 17th May), week 9 (w/c Sat 24th May), week 12 (w/c Sat 14th June), week 18 (w/c Sat 26th July), week 22 (w/c Sat 23rd Aug), week 23 (w/c Sat 30 Aug), and week 24 (w/c Sat 6th Sept) possessions to be constrained to 0045 Sun to 0815 Sun BLOCKED only.

301.3 Coventry North Jn to Birmingham International South Jn, Amend footnote to read:   	Weekend week 8 (w/c Sat 17th May), week 9 (w/c Sat 24th May), week 12 (w/c Sat 14th June), week 18 (w/c Sat 26th July), week 22 (w/c Sat 23rd Aug), week 23 (w/c Sat 30 Aug), and week 24 (w/c Sat 6th Sept) possessions to be constrained to 0045 Sun to 0815 Sun BLOCKED only.

301.4 Birmingham International South Jn to Proof House Jn, Amend footnote to read:

	Weekend week 8 (w/c Sat 17th May), week 9 (w/c Sat 24th May), week 12 (w/c Sat 14th June), week 18 (w/c Sat 26th July), week 22 (w/c Sat 23rd Aug), week 23 (w/c Sat 30 Aug), and week 24 (w/c Sat 6th Sept) possessions to be constrained to 0045 Sun to 0815 Sun BLOCKED only.

301.8 Soho North Jn and Galton Jn, Add footnote to read:

	Weekend week 8 (w/c Sat 17th May), week 9 (w/c Sat 24th May), week 12 (w/c Sat 14th June), possessions to be constrained to 0045 Sun to 0845 Sun BLOCKED only.

301.9 Galton Jn and Wolverhampton Crane St Jn, Add footnote to read:

	Weekend week 8 (w/c Sat 17th May), week 9 (w/c Sat 24th May), week 12 (w/c Sat 14th June), possessions to be constrained to 0045 Sun to 0845 Sun BLOCKED only.

MD315 STECHFORD SOUTH JN TO ASTON SOUTH JN

315.1 Stechford South Jn and Aston South Jn, Add footnote to read:   	Weekend week 8 (w/c Sat 17th May), week 9 (w/c Sat 24th May), week 12 (w/c Sat 14th June), week 18 (w/c Sat 26th July), week 22 (w/c Sat 23rd Aug), week 23 (w/c Sat 30 Aug), and week 24 (w/c Sat 6th Sept) possessions to be constrained to 0045 Sun to 0815 Sun BLOCKED only.

MD320 PROOF HOUSE JN TO BUSHBURY JN (VIA BESCOT)

320.2 Aston South Jn and Aston North Jn, Add footnote to read:   	Weekend week 18 (w/c Sat 26th July), week 22 (w/c Sat 23rd Aug), week 23 (w/c Sat 30 Aug), and week 24 (w/c Sat 6th Sept) possessions to be constrained to 0015 Sun to 0850 Sun BLOCKED only.

320.3 Aston North Jn and Perry Barr North Jn, Amend footnote to read:   	Weekend week 18 (w/c Sat 26th July), week 22 (w/c Sat 23rd Aug), week 23 (w/c Sat 30 Aug), and week 24 (w/c Sat 6th Sept) possessions to be constrained to 2345 Sat to 0945 Sun BLOCKED only.

320.4 Perry Barr North Jn and Newton Jn, Add footnote to read:   	Weekend week 18 (w/c Sat 26th July), week 22 (w/c Sat 23rd Aug), week 23 (w/c Sat 30 Aug), and week 24 (w/c Sat 6th Sept) possessions to be constrained to 2345 Sat to 0950 Sun BLOCKED only.

320.5 Newton Jn and Bescot Jn, Add footnote to read:   	Weekend week 18 (w/c Sat 26th July), week 22 (w/c Sat 23rd Aug), week 23 (w/c Sat 30 Aug), and week 24 (w/c Sat 6th Sept) possessions to be constrained to 2345 Sat to 0950 Sun BLOCKED only.

320.6 Bescot Jn and Darlaston Jn, Add footnote to read:   	Weekend week 18 (w/c Sat 26th July), week 22 (w/c Sat 23rd Aug), week 23 (w/c Sat 30 Aug), and week 24 (w/c Sat 6th Sept) possessions to be constrained to 0001 Sun to 0900 Sun BLOCKED only.

320.7 Darlaston Jn and Portobello Jn, Add footnote to read:   	Weekend week 18 (w/c Sat 26th July), week 22 (w/c Sat 23rd Aug), week 23 (w/c Sat 30 Aug), and week 24 (w/c Sat 6th Sept) possessions to be constrained to 0045 Sun to 0900 Sun BLOCKED only.

320.8 Portobello Jn and Bushbury Jn, Add footnote to read:   	Weekend week 18 (w/c Sat 26th July), week 22 (w/c Sat 23rd Aug), week 23 (w/c Sat 30 Aug), and week 24 (w/c Sat 6th Sept) possessions to be constrained to 2300 Sat to 0915 Sun BLOCKED only.

MD355 LICHFIELD TV JN TO LICHFIELD TRENT VALLEY

355.1 Lichfield TV Jn and Lichfield Trent Valley, Weekend period ‘D’ amended to read 1000 Sat to 0930 Sun All BLOCKED (V6.2 Period D1 2000 Sat -0830 Sun, Period D2 2330 Sat-0830 Sun) (Network Rail Request).

Clashing Possessions:

Weeks 10, 11, 12, 13 Freightliner diversions cross country.

NW1001 ARMITAGE JN TO PRESTON FYLDE JN

1001.7 Norton Bridge North Jn and Crewe South Jn, Weekend period ‘D’ amend footnote to read:   	Weekend week 17 (w/c Sat 19th July) and week 18 (w/c Sat 26th July), either Down Slow or Up Fast to be available between 0815 Sun and 2300 Sun and week 22 (w/c Sat 23rd Aug), week 23 (w/c Sat 30 Aug), Fast line possession times to be constrained to 2315 Sat to 0815 Sun

1001.9 Crewe North Jn and Winsford South Jn, Weekend period ‘D’ amended to read 0001 Sun to 0910 Sun BLOCKED until Sunday 13th July 2008  and 2300 Sat to 1030 Sun BLOCKED from Saturday 19th July 2008 (V6.2 Period D 0001 Sun-0910 Sun)

1001.10 Winsford South Jn and Weaver Jn, Weekend period ‘D’ amended to read 0001 Sun to 0910 Sun BLOCKED until Sunday 13th July 2008  and 2300 Sat to 1030 Sun BLOCKED from Saturday 19th July 2008 (V6.2 Period D 0001 Sun-0910 Sun)

1001.11 Weaver Jn and Acton Grange Jn, Weekend period ‘D’ amended to read 2345 Sat to 0900 Sun BLOCKED until Sunday 13th July 2008  and 2300 Sat to 1030 Sun BLOCKED from Saturday 19th July 2008 (V6.2 Period D 2345 Sat-0900 Sun)

NW2001 WEAVER JN TO LIVEPOOL LIME STREET

2001.1 Weaver Jn and Sutton Weaver GF, Weekend period ‘D’ amended to read 0001 Sun to 0945 Sun BLOCKED until Sunday 13th July 2008 and 2300 Sat to 1030 Sun BLOCKED from Saturday 19th July 2008 (V6.2 Period D 0001 Sun-0945 Sun)

2001.2 Sutton Weaver GF and Ditton East Jn, Weekend period ‘D’ amended to read 0010 Sun to 0925 Sun BLOCKED until Sunday 13th July 2008  and 2300 Sat to 1030 Sun BLOCKED from Saturday 19th July 2008 (V6.2 Period D 0010 Sun-0925 Sun)

Existing LNW 2008 ROTR section 7 possession to be amended to read:

PPS Ref: P2008/ 835272

Week 9 Saturday 24th to Thursday 29th May 2008

At/Between: Atherstone and Armitage Jn

Lines: All BLOCKED

Times: 0030 Sat to 0530 Thu (currently 0030 Sat-0530 Tue – note 0530 Wed at Nuneaton (P2008/834696))

Work: Track & OLE in Preparation for signalling commissioning

Traffic Remarks: TRAINS TO BE DIVERTED VIA THE WEST MIDLANDS. ACCESS RUGELEY POWER STATION FROM THE HEDNESFORD DIRECTION ONLY.

Clashing Possessions:

Section 5 Possessions W/Th Trent Valley Jn to Stechford, Stechford to Aston South Jn and Aston South Jn to Bescot Jn.

LNW 2008 ROTR additional possession request for section 7:

PPS Ref: P2008/xxxxxx

Week 12 Saturday 14th to Wednesday 18th June 2008

At/Between: Hillmorton Jn and Shilton/Brandon

Lines: All BLOCKED

Times: 0001 Sat to 0500 Tue

and

At/Between: Trent Valley Jn and Shilton

Lines: All BLOCKED

Times: 0500 Tue to 0500 Wed

Work: Stage G Signalling Commissioning Follow-up.

Traffic Remarks: 0001 SAT TO 0500 TUE TRAINS TO START/TERMINATE FROM THE SOUTH AT NORTHAMPTON. TRAINS TO/FROM THE NORTH TO START/TERMINATE AT COVENTRY OR BIRMINGHAM INTERNATIONAL. TRAINS TO BE DIVERTED VIA ACTON WELLS, ACTON MAIN LINE, EALING BROADWAY, GREENFORD, SOUTH RUISLIP, CHILTERNS, BANBURY AND LEAMINGTON OR NORTH LONDON LINE, KINGS CROSS INCLINE AND ECML. 0500 TUE TO 0500 WED TRAINS TO BE DIVERTED VIA WEST MIDLANDS.

Clashing Possessions:

P2008/993662 Brandon to Stechford Jn – 29hrs Sunday possession

P2008/993659 Galton Jn and Monmore Green – 29hrs Sunday possession

P2008/862843 Oxford and Aynho Jn – 29hrs Sunday possession

P2008/860655 Grantham to Retford 1200 Sat to 1200 Sun BLOCKED

Section 4 midweek possessions be lifted between South Ruislip and Aynho Jn.

LNW 2008 ROTR additional possession request for section 7:

PPS Ref: P2008/xxxxxx

Week 15 Saturday 5th to Sunday 6th July 2008

At/Between: Preston Fylde Jn and Lancaster South Jn

Lines: All BLOCKED

Times: 2100 Sat to 1300 Sun

Work: Line Speed Enhancements

Traffic Remarks: TRAINS TO START/TERMINATE AT PRESTON OR LANCASTER, RAIL REPLACEMENT ROAD SERVICE TO OPERATE.

PPS Ref: P2008/xxxxxx

Week 15 Saturday 5th to Monday 7th July 2008

At/Between: Carnforth North Jn and Penrith

Lines: All BLOCKED

Times: 0400 Sat to 0430 Mon

Work: Line Speed Enhancements

Traffic Remarks: TRAINS TO START/TERMINATE AT LANCASTER OR PENRITH, RAIL REPLACEMENT ROAD SERVICE TO OPERATE. FREIGHT TO BE RE-TIMED. NO ACCESS HARDENDALE AND HARRISON SIDINGS. SUN/MON SLEEPER TO BE DIVERTED VIA ECML

Clashing Possessions:

Settle to Carlisle Summer Blockade

East Coast Main Line, Sun/Mon sleepers via ECML

LNW 2008 ROTR additional possession request for section 7:

PPS Ref: P2008/xxxxxx

Week 16 Saturday 12th to Sunday 13th July 2008

At/Between: Preston Fylde Jn and Lancaster South Jn

Lines: All BLOCKED

Times: 2100 Sat to 1300 Sun

Work: Line Speed Enhancements

Traffic Remarks: TRAINS TO START/TERMINATE AT PRESTON OR LANCASTER, RAIL REPLACEMENT ROAD SERVICE TO OPERATE.

PPS Ref: P2008/xxxxxx

Week 16 Saturday 12th to Monday 14th July 2008

At/Between: Carnforth North Jn and Penrith

Lines: All BLOCKED

Times: 0400 Sat to 0430 Mon

Work: Line Speed Enhancements

Traffic Remarks: TRAINS TO START/TERMINATE AT LANCASTER OR PENRITH, RAIL REPLACEMENT ROAD SERVICE TO OPERATE. NO ACCESS HARDENDALE AND HARRISON SIDINGS. FREIGHT TO BE RE-TIMED. SUN/MON SLEEPER TO BE DIVERTED VIA ECML

Clashing Possessions:

Settle to Carlisle Summer Blockade

East Coast Main Line, Sun/Mon sleepers via ECML

LNW 2008 ROTR additional possession request for section 7:

PPS Ref: P2008/xxxxxx

Week 17 Saturday 19th to Sunday 20th July 2008

At/Between: Preston Fylde Jn and Lancaster South Jn

Lines: All BLOCKED

Times: 2100 Sat to 1300 Sun

Work: Line Speed Enhancements

Traffic Remarks: TRAINS TO START/TERMINATE AT PRESTON OR LANCASTER, RAIL REPLACEMENT ROAD SERVICE TO OPERATE.

PPS Ref: P2008/xxxxxx

Week 17 Saturday 19th to Monday 21st July 2008

At/Between: Carnforth North Jn and Penrith

Lines: All BLOCKED

Times: 0400 Sat to 0430 Mon

Work: Line Speed Enhancements

Traffic Remarks: TRAINS TO START/TERMINATE AT LANCASTER OR PENRITH, RAIL REPLACEMENT ROAD SERVICE TO OPERATE. NO ACCESS HARDENDALE AND HARRISON SIDINGS. FREIGHT TO BE RE-TIMED. SUN/MON SLEEPER TO BE DIVERTED VIA ECML

Clashing Possessions:

Settle to Carlisle Summer Blockade

East Coast Main Line, Sun/Mon sleepers via ECML

LNW 2008 ROTR additional possession request for section 7:

PPS Ref: P2008/xxxxxx

Week 17 Sunday 20th to Monday 21st July 2008

At/Between: Crewe North Jn and Cheadle Hulme

Lines: All BLOCKED

Times: 0030 Sun to 0515 Mon

Work: Line Speed Enhancements

Traffic Remarks: TRAINS TO BE DIVERTED VIA STOKE ON TRENT AND MACCLESFIELD OR VIA CHAT MOSS AND WCML. NORTHERN RAIL SERVICES TO DIVERT VIA STYAL AND START/TERMINATE AT WILMSLOW. RAIL REPLACEMENT ROAD SERVICES TO OPERATE.

LNW 2008 ROTR additional possession request for section 7:

PPS Ref: P2008/xxxxxx

Week 18 Saturday 26th to Sunday 27th July 2008

At/Between: Preston Fylde Jn and Lancaster South Jn

Lines: All BLOCKED

Times: 2100 Sat to 1300 Sun

Work: Line Speed Enhancements

Traffic Remarks: TRAINS TO START/TERMINATE AT PRESTON OR LANCASTER, RAIL REPLACEMENT ROAD SERVICE TO OPERATE.

PPS Ref: P2008/xxxxxx

Week 18 Saturday 26th to Monday 28th July 2008

At/Between: Carnforth North Jn and Penrith

Lines: All BLOCKED

Times: 0400 Sat to 0430 Mon

Work: Line Speed Enhancements

Traffic Remarks: TRAINS TO BE DIVERTED VIA SETTLE AND APPLEBY. TRAINS TO START/TERMINATE AT LANCASTER OR PENRITH, RAIL REPLACEMENT ROAD SERVICE TO OPERATE. NO ACCESS HARDENDALE AND HARRISON SIDINGS. FREIGHT TO BE RE-TIMED. SUN/MON SLEEPER TO BE DIVERTED VIA ECML

LNW 2008 ROTR additional possession request for section 7:

PPS Ref: P2008/xxxxxx

Week 18 Sunday 27th to Monday 28th July 2008

At/Between: Crewe North Jn and Cheadle Hulme

Lines: All BLOCKED

Times: 0030 Sun to 0515 Mon

Work: Line Speed Enhancements

Traffic Remarks: TRAINS TO BE DIVERTED VIA STOKE ON TRENT AND MACCLESFIELD OR VIA CHAT MOSS AND WCML. NORTHERN RAIL SERVICES TO DIVERT VIA STYAL AND START/TERMINATE AT WILMSLOW. RAIL REPLACEMENT ROAD SERVICES TO OPERATE..

LNW 2008 ROTR additional possession request for section 7:

PPS Ref: P2008/xxxxxx

Week 19 Saturday 2nd to Sunday 3rd August 2008

At/Between: Preston Fylde Jn and Lancaster South Jn

Lines: All BLOCKED

Times: 2100 Sat to 1300 Sun

Work: Line Speed Enhancements

Traffic Remarks: TRAINS TO START/TERMINATE AT PRESTON OR LANCASTER, RAIL REPLACEMENT ROAD SERVICE TO OPERATE.

Existing LNW 2008 ROTR section 7 possession to be amended to read:

PPS Ref: P2008/869953

Week 21 Friday 15th to Monday 18th August 2008

At/Between: Denbigh Hall North Jn and Hanslope Jn

Lines: Down and Up Slow BLOCKED

Times: 2200 Fri to 0800 Sat

and

At/Between: Denbigh Hall North Jn and Hanslope Jn

Lines: All BLOCKED

Times: 0800 Sat to 0300 Mon

Work: Install S&C

Traffic Remarks:

2200 FRI TO 0800 SAT TRAINS TO BE TRAVEL OVER FAST LINES. 2200 FRI TO 0300 MON NO ACCESS MILTON KEYNES CENTRAL BAY PLATFORM AND WOLVERTON RAILCARE SIDINGS. 0800 SAT TO 0300 MON TRAINS TO START/TERMINATE FROM THE SOUTH AT BLETCHLEY. TRAINS TO/FROM THE NORTH TO START/TERMINATE AT COVENTRY OR BIRMINGHAM INTERNATIONAL. TRAINS TO BE DIVERTED VIA ACTON WELLS, ACTON MAIN LINE, EALING BROADWAY, GREENFORD, SOUTH RUISLIP, CHILTERNS, BANBURY AND LEAMINGTON OR NORTH LONDON LINE, KINGS CROSS INCLINE AND ECML.

Clashing Possessions:

P2008/8708652 33hrs Fasts BLOCKED Watford Sth Jn and Bletchley Sth Jn - will need to reduce to Watford to Ledburn Jn (4 lines access required Bletchley),

P2008/863603 52hrs all BLOCKED Coventry Nth Jn and Proof House Jn, P2008/1035393 Mill Lane Jn and Daventry 36 hrs,

P2008/1023299 – Aston and Bescot Middle – 29hrs,

P2008/1037050 – Darlaston Jn and Bushbury Jn – 29hrs,

P2008/1023331 – Soho Road – 29hrs,

P2008/863737 – Leamington Spa and Coventry – 52hrs,

P2008/934757 27hrs Marylebone to Neasden Jn, P2008/957402 52hrs Wembley and Northolt Jn,

P2008/862492 12hrs High Wycombe and Bicester North,

P2008/862507 12hrs Aylesbury. Acton West to Slough Relief lines BLOCKED 2145 Sat to 0455 Mon

Existing LNW 2008 ROTR section 7 possession to be amended to read:

PPS Ref: P2008/836253

Week 22 Saturday 23rd to Wednesday 27th August 2008

At/Between: Hillmorton Jn and Shilton

Lines: All BLOCKED

and

At/Between: Rugby Trent Valley Jn and Coventry South Jn

Lines: Down and Up Coventry BLOCKED

Times: 0130 Sat to 0500 Wed

Work: Preparation for signalling commissioning

Traffic Remarks: 0130 SAT TO 1000 SAT TRAINS FROM THE SOUTH TO START/TERMINATE AT NORTHAMPTON, BETWEEN 1000 SAT TO 0100 SUN AT BLETCHLEY, 0830 SUN TO 1200 SUN AT WATFORD JN, FROM 1200 SUN TO 0300 TUE AT HEMEL HEMPSTEAD, FROM 0300 TUE TO 0500 WED AT NORTHAMPTON. 0300 SAT TO 0500 WED TRAINS TO/FROM THE NORTH TO START/TERMINATE AT COVENTRY OR BIRMINGHAM INTERNATIONAL. 0300 SAT TO 1000 SAT AND 0300 TUE TO 0500 WED ACCESS NORTHAMPTON STATION, NORTHAMPTON UP YARD, KINGS HEATH TMD, DAVENTRY IRFT FROM THE SOUTH ONLY. 0300 SAT TO 0300 TUE NO ACCESS NORTHAMPTON STATION, NORTHAMPTON UP SIDE YARD, KINGS HEATH TMD AND DAVENTRY IRFT. 0300 SAT TO 0500 WED TRAINS TO BE DIVERTED VIA ACTON WELLS, ACTON MAIN LINE, EALING BROADWAY, GREENFORD, SOUTH RUISLIP, CHILTERNS, BANBURY AND LEAMINGTON OR NORTH LONDON LINE, KINGS CROSS INCLINE AND ECML.

Clashing Possessions:

Section 4 weekend Derby to Barton South Jn to be lifted

Section 4 midweek possessions be lifted between South Ruislip and Aynho Jn.

Section 5 midweek M/T, T/W Leamington to Bordesley Jn

Existing LNW 2008 ROTR section 7 possession to be amended to read:

PPS Ref: P2008/1006111

Week 22 to 24 Saturday 23rd August to Monday 8th September 2008

At/Between: Shilton and Colwich Jn

Lines: All BLOCKED

and

At/Between: Hawksbury Lane SB and Nuneaton South Jn

Lines: All BLOCKED

Times: 0030 Sat 23/8 to 0530 Mon 8/9 (currently 0030 Sat 23/8 to 0530 Mon 1/9)

and

At/Between: Croft Sidings and Abbey Jn

Lines: Down and Up Hinckley BLOCKED

and

At/Between: Nuneaton North Jn and Daw Mill

Lines: All BLOCKED

Times: 0030 Sat 23/8 to 0530 Tue 26/8

Work: Signalling Commissioning (Nuneaton Interlockings – North, South, East, West and Atherstone).

Traffic Remarks: 0030 SAT 23/8 TO 0530 MON 8/9

TRAINS TO BE DIVERTED VIA WEST MIDLANDS. RAIL REPLACEMENT ROAD SERVICE TO OPERATE BETWEEN COVENTRY AND NUNEATON. ACCESS AVAILABLE BEDWORTH CALOR GAS SIDING FROM THE COVENTRY DIRECTION ONLY.

0030 SAT 23/8 TO 0530 TUE 26/8

TRAINS TO BE DIVERTED VIA TRENT, BURTON ON TRENT AND TAMWORTH. NO ACESS NUNEATON STATION. ACCESS DAW MILL COLLIERY FROM THE WHITACRE JN DIRECTION ONLY. BIRMINGHAM TO PETERBOROUGH SERVICES TO START/TERMINATE AT LEICESTER, RAIL REPLACEMENT ROAD SERVICE TO OPERATE BETWEEN BIRMINGHAM AND LEICESTER AND COVENTRY AND NUNEATON.

0530 TUE 26/8 TO 0530 MON 8/9

AT NUNEATON ACCESS AVAILABLE BETWEEN ARLEY AND HINCKLEY VIA PLATFORMS 6 & 7.

Clashing Possessions:

Week 22, 23 and 24 Section 4 Possessions Trent Valley Jn to Stechford, Stechford to Aston South Jn and Aston South Jn to Bescot Jn.

Week 22 P2008/915664 Stechford-New St 29 hrs

Week 22 P2008/1023484 Aston North-Tame Bridge 29 hrs

Week 22 P2008/862449 Bescot Jn-Bushbury Jn 29 hrs

Week 23 P2008/915667 Stechford-New St 29 hrs

Week 23 P2008/1023393 Aston North-Tame Bridge 29 hrs

Week 23 P2008/1037868 Bescot Jn-Bushbury Jn 29 hrs

Week 24 P2008/870254 At Stafford - 18hrs (11hrs all BLOCKED)

Week 24 P2008/915691 Stechford North Jn and Birmingham New Street – 52hrs

Week 24 P2008/934508 Wolves North Jn and Penkridge – 18hrs

Existing LNW 2008 ROTR section 7 possession to be amended to read:

PPS Ref: P2008/8636351

Week 23 Saturday 30th August to Monday 1st September 2008

At/Between: Hilmorton Jn and Shilton/Brandon

Lines: All BLOCKED

Times: 0030 Sat to 0500 Mon (Currently 0300 Sat-0530 Mon)

Work: Preparation for signalling commissioning.

Traffic Remarks: Amended Train Working (Possession already agreed as 0300 Sat start)

LNW 2008 ROTR additional possession request for section 7:

PPS Ref: P2008/xxxxxx

Week 25 Saturday 13th to Monday 15th September 2008

At/Between: Crewe North Jn and Preston Brook Tunnel

Lines: All BLOCKED

and

At/Between: Weaver Jn and Ditton East Jn

Lines: All BLOCKED

Times: 0020 Sat to 0215 Mon

Traffic Remarks: 0020 SAT TO 1200 SAT TRAINS TO BE DIVERTED VIA WILMSLOW, STOCKPORT, MANCHESTER AND CHAT MOSS. 1200 SAT TO 0215 MON TRAINS TIMETABLED VIA MANCHESTER. FRI/SAT SLEEPERS TO DIVERT VIA ECML.

LNW 2008 ROTR additional possession request for section 7:

PPS Ref: P2008/xxxxxx

Week 25 Sunday 14th to Monday 15th September 2008

At/Between: Colwich Jn and Macclesfield

Lines: All BLOCKED

Times: 0005 Sun to 0530 Mon

Work: Line Speed Enhancements

Traffic Remarks: TRAINS TO BE DIVERTED VIA CREWE AND WILMSLOW. NORTHERN RAIL SERVICES TO SHUTTLE BETWEEN MACCLESFIELD AND MANCHESTER. EAST MIDLANDS TRAIN SERVICES TO START/TERMINATE AT UTTOXETER. NO ACCESS MARCROFT ENGINEERING SIDINGS, STOKE ON TRENT STATION,  LNW YARD AND LONGPORT FREIGHT DEPOT. RAIL REPLACEMENT ROAD SERVICES TO OPERATE BETWEEN STAFFORD, STOKE AND MACCLESFIELD AND UTTOXETER, STOKE AND CREWE.

LNW 2008 ROTR additional possession request for section 7:

PPS Ref: P2008/xxxxxx

Week 26 Saturday 20th to Monday 22nd September 2008

At/Between: Crewe North Jn and Preston Brook Tunnel

Lines: All BLOCKED

and

At/Between: Weaver Jn and Ditton East Jn

Lines: All BLOCKED

Times: 0020 Sat to 0215 Mon

Traffic Remarks: 0020 SAT TO 1200 SAT TRAINS TO BE DIVERTED VIA WILMSLOW, STOCKPORT, MANCHESTER AND CHAT MOSS. 1200 SAT TO 0215 MON TRAINS TIMETABLED VIA MANCHESTER. FRI/SAT SLEEPERS TO DIVERT VIA ECML.

LNW 2008 ROTR additional possession request for section 7:

PPS Ref: P2008/xxxxxx

Week 26 Sunday 21st to Monday 22nd September 2008

At/Between: Colwich Jn and Macclesfield

Lines: All BLOCKED

Times: 0005 Sun to 0530 Mon

Work: Line Speed Enhancements

Traffic Remarks: TRAINS TO BE DIVERTED VIA CREWE AND WILMSLOW. NORTHERN RAIL SERVICES TO SHUTTLE BETWEEN MACCLESFIELD AND MANCHESTER. EAST MIDLANDS TRAIN SERVICES TO START/TERMINATE AT UTTOXETER. NO ACCESS MARCROFT ENGINEERING SIDINGS, STOKE ON TRENT STATION,  LNW YARD AND LONGPORT FREIGHT DEPOT. RAIL REPLACEMENT ROAD SERVICES TO OPERATE BETWEEN STAFFORD, STOKE AND MACCLESFIELD AND UTTOXETER, STOKE AND CREWE.

LNW 2008 ROTR additional possession request for section 7:

PPS Ref: P2008/xxxxxx

Week 27 Sunday 28th to Monday 29th September 2008

At/Between: Colwich Jn and Macclesfield

Lines: All BLOCKED

Times: 0005 Sun to 0530 Mon

Work: Line Speed Enhancements

Traffic Remarks: TRAINS TO BE DIVERTED VIA CREWE AND WILMSLOW. NORTHERN RAIL SERVICES TO SHUTTLE BETWEEN MACCLESFIELD AND MANCHESTER. EAST MIDLANDS TRAIN SERVICES TO START/TERMINATE AT UTTOXETER. NO ACCESS MARCROFT ENGINEERING SIDINGS, STOKE ON TRENT STATION,  LNW YARD AND LONGPORT FREIGHT DEPOT. RAIL REPLACEMENT ROAD SERVICES TO OPERATE BETWEEN STAFFORD, STOKE AND MACCLESFIELD AND UTTOXETER, STOKE AND CREWE.

LNW 2008 ROTR additional possession request for section 7:

PPS Ref: P2008/xxxxxx

Week 28 Sunday 5th to Monday 6th October 2008

At/Between: Colwich Jn and Macclesfield

Lines: All BLOCKED

Times: 0005 Sun to 0530 Mon

Work: Line Speed Enhancements

Traffic Remarks: TRAINS TO BE DIVERTED VIA CREWE AND WILMSLOW. NORTHERN RAIL SERVICES TO SHUTTLE BETWEEN MACCLESFIELD AND MANCHESTER. EAST MIDLANDS TRAIN SERVICES TO START/TERMINATE AT UTTOXETER. NO ACCESS MARCROFT ENGINEERING SIDINGS, STOKE ON TRENT STATION,  LNW YARD AND LONGPORT FREIGHT DEPOT. RAIL REPLACEMENT ROAD SERVICES TO OPERATE BETWEEN STAFFORD, STOKE AND MACCLESFIELD AND UTTOXETER, STOKE AND CREWE.

LNW 2008 ROTR additional possession request for section 7:

PPS Ref: P2008/xxxxxx

Week 28 Saturday 4th to Tuesday 7th October 2008

At/Between: Hanslope Jn and Daventry North Jn

Lines: All BLOCKED

Times: 1000 Sat to 2305 Sat

and

At/Between: Hanslope Jn (inc) and Hillmorton Jn (inc)

Lines: All BLOCKED

Times: 2305 Sat to 0905 Sun

and

At/Between: Hanslope Jn and Hillmorton Jn (inc) (via Northampton)

Lines: All BLOCKED

Times: 0905 Sun to 1800 Sun

and

At/Between: Northampton North Jn and Hillmorton Jn (inc)

Lines: All BLOCKED

Times: 1800 Sun to 0600 Mon

and

At/Between: Northampton North Jn and Hillmorton Jn

Lines: All BLOCKED

Times: 0600 Mon to 0500 Tue

Work: Signal commissioning and re-control

Traffic Remarks:

1000 SAT TO 2305 SAT AND 0905 SUN TO 0500 TUE TRAINS TO BE DIVERTED VIA WEEDON. TRAINS TO START/TERMINATE AT MILTON KEYNES, RAIL REPLACEMENT ROAD SERVICE TO OPERATE. NORTHAMPTON TO BIRMINGHAM SERVICES TO OPERATE BETWEEN COVENTRY AND BIRMINGHAM ONLY, RAIL REPLACEMENT ROAD SERVICE TO OPERATE. 1000 SAT TO 1800 SUN NO ACCESS NORTHAMPTON STATION, NORTHAMPTON RIVERSIDE SIDINGS, KINGS HEATH DEPOT AND NORTHAMPTON YARD. 2305 SAT TO 0905 SUN AMENDED TRAIN WORKING, RAIL REPLACEMENT ROAD SERVICE TO OPERATE. 2305 SAT TO 0500 TUE

NO ACCESS DAVENTRY IRFT.1800 SUN TO 0600 TUE ACCESS KINGS HEATH TMD AND NORTHAMPTON YARD FROM THE NORTHAMPTON DIRECTION ONLY.

LNW 2008 ROTR additional possession request for section 7:

PPS Ref: P2008/xxxxxx

Week 31 Saturday 25th to Tuesday 28th October 2008

At/Between: Rugby Trent Valley Jn and Atherstone

Lines: All BLOCKED

Times: 0030 Sat to 0530 Tue

and

At/Between: Hawkesbury Lane

Lines: All BLOCKED

Times: 0030 Sat to 0530 Tue

and

At/Between: Croft to Daw Mill

Lines: All BLOCKED

Times: 0030 Sat to 0530 Tue

Work: Nuneaton stage 2 commissioning Firewall possessions

Traffic Remarks: TRAINS TO BE DIVERTED VIA THE WEST MIDLANDS. TRAINS TO BE DIVERTED VIA TRENT, BURTON ON TRENT AND TAMWORTH. NO ACESS NUNEATON STATION. ACCESS DAW MILL COLLIERY FROM THE WHITACRE JN DIRECTION ONLY. BIRMINGHAM TO PETERBOROUGH SERVICES TO START/TERMINATE AT LEICESTER, RAIL REPLACEMENT ROAD SERVICE TO OPERATE BETWEEN BIRMINGHAM AND LEICESTER AND COVENTRY AND NUNEATON.

Clashing Possessions:

Section 5 Possessions W/Th Trent Valley Jn to Stechford, Stechford to Aston South Jn and Aston South Jn to Bescot Jn.

P862844 Oxford-Aynho 2300 Sat-0500 Mon

LNW 2008 ROTR additional possession request for section 7:

PPS Ref: P2008/xxxxxx

Week 34 Saturday 15th to Tuesday 18th November 2008

At/Between: Hanslope Jn and Daventry North Jn

Lines: All BLOCKED

Times: 1000 Sat to 2305 Sat

and

At/Between: Hanslope Jn (inc) and Hillmorton Jn (inc)

Lines: All BLOCKED

Times: 2305 Sat to 0905 Sun

and

At/Between: Hanslope Jn and Hillmorton Jn (inc) (via Northampton)

Lines: All BLOCKED

Times: 0905 Sun to 1800 Sun

and

At/Between: Northampton North Jn and Hillmorton Jn (inc)

Lines: All BLOCKED

Times: 1800 Sun to 0600 Mon

and

At/Between: Northampton North Jn and Hillmorton Jn

Lines: All BLOCKED

Times: 0600 Mon to 0500 Tue

Work: Signal commissioning and re-control at Northampton, Firewall possession.

Traffic Remarks:

1000 SAT TO 2305 SAT AND 0905 SUN TO 0500 TUE

TRAINS TO BE DIVERTED VIA WEEDON. TRAINS TO START/TERMINATE AT MILTON KEYNES, RAIL REPLACEMENT ROAD SERVICE TO OPERATE. NORTHAMPTON TO BIRMINGHAM SERVICES TO OPERATE BETWEEN COVENTRY AND BIRMINGHAM ONLY, RAIL REPLACEMENT ROAD SERVICE TO OPERATE.

1000 SAT TO 1800 SUN

NO ACCESS NORTHAMPTON STATION, NORTHAMPTON RIVERSIDE SIDINGS, KINGS HEATH DEPOT AND NORTHAMPTON YARD.

2305 SAT TO 0905 SUN

AMENDED TRAIN WORKING, RAIL REPLACEMENT ROAD SERVICE TO OPERATE.

2305 SAT TO 0500 TUE

NO ACCESS DAVENTRY IRFT.

1800 SUN TO 0600 TUE

ACCESS KINGS HEATH TMD AND NORTHAMPTON YARD FROM THE NORTHAMPTON DIRECTION ONLY.

Existing LNW 2008 ROTR section 7 possession to be amended to read:

PPS Ref: P2008/1007054 and 1007055

Week 35/36 Friday 21st November to Monday 1st December 2008

At/Between: Kilsby North and Shilton

Lines: All BLOCKED

Times: 2315 Fri-0530 Mon

SLW/Bidirectional over line?? 2315 Fri/or 0015 Sat-0700 Sat

Week 36 0700 Sat – 0530 Mon

Existing LNW 2008 ROTR section 7 possession to be WITHDRAWN:

PPS Ref: P2008/836311

Week 35/36 Monday 24th to Friday 28th November 2008

At/Between: Long Lawford/High Oaks and Hillmorton Jn

Lines Affected: Up Coventry, Up Main/Fast, Up Trent Valley Slow, Up & Down Engine Line BLOCKED

Times: 0530 Mon 24/11 to 2300 Friday 28/11

and

At/Between: High Oaks Jn and Hillmorton Jn

Lines affected: Up Slow, Platform 4 Blocked

Times: 1200 MTWTh to 0500 TWThF.

LNW 2008 ROTR additional possession request for section 7:

PPS Ref: P2008/1007055

Week 36 Saturday 29th November to Monday 1st December 2008

At/Between: Kilsby North and Shilton

Lines: All BLOCKED

and

At/Between: Daventry South Jn and Hillmorton Jn

Lines: Down and Up Northampton BLOCKED

and

At/Between: Rugby Trent Valley Jn and Coventry South Jn

Lines: Down and Up Coventry BLOCKED

Times: 0700 Sat 29/11 to 0530 Mon 1/12 (currently 2315 Fri 28/11 to 0530 Mon 1/12)

Work: Remodelling and SSI Signalling Testing and Commissioning.

Traffic Remarks: TRAINS FROM THE SOUTH TO START/TERMINATE AT NORTHAMPTON, TRAINS TO/FROM THE NORTH TO START/TERMINATE AT COVENTRY OR BIRMINGHAM INTERNATIONAL, RAIL REPLACEMENT ROAD SERVICE TO OPERATE. NO ACCESS BETWEEN THE NORTH AND KINGS HEATH TMD, NORTHAMPTON YARD AND DAVENTRY IRFT. TRAINS TO BE DIVERTED VIA ACTON WELLS, ACTON MAIN LINE, EALING BROADWAY, GREENFORD, SOUTH RUISLIP, CHILTERNS, BANBURY AND LEAMINGTON OR NORTH LONDON LINE, KINGS CROSS INCLINE AND ECML.

LNW 2008 ROTR additional possession request for section 7:

PPS Ref: P2008/xxxxxx

Week 37 Saturday 6th to Sunday 7th December 2008

At/Between: Hillmorton Jn and Shilton

Lines: All BLOCKED

and

At/Between: Trent Valley Jn and Brandon

Lines: Down and Up Coventry BLOCKED

Times: 1030 Sat to 2100 Sun

Work: Contingency for stage J signal commissioning

Traffic Remarks: TRAINS TO START/TERMINATE FROM THE SOUTH AT NORTHAMPTON. TRAINS TO/FROM THE NORTH TO START/TERMINATE AT COVENTRY OR BIRMINGHAM INTERNATIONAL. RAIL REPLACEMENT ROAD SERVICE TO OPERATE. TRAINS TO BE DIVERTED VIA ACTON WELLS, ACTON MAIN LINE, EALING BROADWAY, GREENFORD, SOUTH RUISLIP, CHILTERNS, BANBURY AND LEAMINGTON OR NORTH LONDON LINE, KINGS CROSS INCLINE AND ECML.

Clashing Possessions:

All lines BLOCKED at Claydon (S&C) on GEML does not permit XC diversion of liners.

LNW 2009 ROTR additional possession request for section 7:

PPS Ref: P2008/xxxxxx

Week 39/40 Wednesday 24th to Monday 29th December 2008

At/Between: Hillmorton Jn and Shilton

Lines: All BLOCKED

and

At/Between: Trent Valley Jn and Brandon

Lines: Down and Up Coventry BLOCKED

Times: 2300 Wed 24/12 to 0300 Mon 29/12

Work: Follow up works from Signalling Commissioning

Traffic Remarks:

2300 WED 24/12 TO 0600 SAT 27/12

CHRISTMAS NO TRAIN PERIOD

0600 SAT 27/12 TO 0300 MON 29/12

TRAINS TO START/TERMINATE FROM THE SOUTH AT NORTHAMPTON. TRAINS TO/FROM THE NORTH TO START/TERMINATE AT COVENTRY OR BIRMINGHAM INTERNATIONAL. RAIL REPLACEMENT ROAD SERVICE TO OPERATE. TRAINS TO BE DIVERTED VIA ACTON WELLS, ACTON MAIN LINE, EALING BROADWAY, GREENFORD, SOUTH RUISLIP, CHILTERNS, BANBURY AND LEAMINGTON OR NORTH LONDON LINE, KINGS CROSS INCLINE AND ECML.

LNW 2009 ROTR additional possession request for section 7:

PPS Ref: P2008/xxxxxx

Week 40/41 Thursday 1st to Monday 5th January 2009

At/Between: Denbigh South Jn and Hanslope Jn

Lines: All BLOCKED

Times: 0001 Thu 1/1 to 0300 Mon 5/1

Work: Signalling commissioning firewall possessions

Traffic Remarks: TRAINS TO START/TERMINATE FROM THE SOUTH AT BLETCHLEY. TRAINS TO/FROM THE NORTH TO START/TERMINATE AT NORTHAMPTON OR RUGBY. TRAINS TO BE DIVERTED VIA ACTON WELLS, ACTON MAIN LINE, EALING BROADWAY, GREENFORD, SOUTH RUISLIP, CHILTERNS, BANBURY AND LEAMINGTON OR NORTH LONDON LINE, KINGS CROSS INCLINE AND ECML.

Clashing Possessions:

0215 Sat to 0500 Mon DCL BLOCKED

Northallerton and Darlington 0600 Sat to 0525 Mon

Section 4 midweek possessions be lifted between South Ruislip and Aynho Jn.

LNW 2009 ROTR additional possession request for section 7:

PPS Ref: P2009/xxxxxx

Week 3 Saturday 12th to Monday 14th April 2009

At/Between: Northampton South Jn and Hillmorton Jn (inc)

Lines: All BLOCKED

and

At/Between: Kilsby and Hillmorton Jn (inc)

Lines: Down and Up Main BLOCKED

Times: 0730 Sat to 1200 Mon

Work: Signalling commissioning and re-control

Traffic Remarks: TRAINS TO START/TERMINATE FROM THE SOUTH AT MILTON KEYNES CENTRAL. TRAINS TO/FROM THE NORTH TO START/TERMINATE AT RUGBY. TRAINS TO BE DIVERTED VIA ACTON WELLS, ACTON MAIN LINE, EALING BROADWAY, GREENFORD, SOUTH RUISLIP, CHILTERNS, BANBURY AND LEAMINGTON OR NORTH LONDON LINE, KINGS CROSS INCLINE AND ECML. NO ACCESS NORTHAMPTON STATION, NORTHAMPTON RIVERSIDE SIDINGS, NORTHAMPTON YARD, KINGS HEATH DEPOT AND DAVENTRY IRFT.

LNW 2009 ROTR additional possession request for section 7:

PPS Ref: P2009/xxxxxx

Week 6 Saturday 2nd to Monday 4th May 2009

At/Between: Northampton South Jn and Hillmorton Jn (inc)

Lines: All BLOCKED

and

At/Between: Kilsby and Hillmorton Jn (inc)

Lines: Down and Up Main BLOCKED

Times: 0730 Sat to 1200 Mon

Work: Signalling commissioning and re-control

Traffic Remarks: TRAINS TO START/TERMINATE FROM THE SOUTH AT MILTON KEYNES CENTRAL. TRAINS TO/FROM THE NORTH TO START/TERMINATE AT RUGBY. TRAINS TO BE DIVERTED VIA ACTON WELLS, ACTON MAIN LINE, EALING BROADWAY, GREENFORD, SOUTH RUISLIP, CHILTERNS, BANBURY AND LEAMINGTON OR NORTH LONDON LINE, KINGS CROSS INCLINE AND ECML. NO ACCESS NORTHAMPTON STATION, NORTHAMPTON RIVERSIDE SIDINGS, NORTHAMPTON YARD, KINGS HEATH DEPOT AND DAVENTRY IRFT.

This letter is in accordance with Access Condition D2.1.10 and relates to Section 3.1 of National Rules of the Plan being the Procedure for Altering Rules of the Route or Rules of the Plan other than through the Twice-Yearly Process Having Effect from a Passenger Change. I look forward to receiving your support for the above proposals by Friday 28th March 2008.

If you require further information or if I can help further, please give me a call.

## Joe Warr

Yours sincerely,

Joe Warr, Senior Network Access Planner.